## Sheet1
Trello Story Name | User Story | Acceptance Criteria | Result | Tester Initials and Date | Comments
Sprint 2
Inject Movie objects into Screening objects | As the product owner I want to inject Movie objects into Screening objects so that I can have multiple Screenings to the same Movie. | **Given** I perform a GET request **when** I view the list of objects returned **then** I expect to see multiple Screening objects with the same Movie information. | PASS | ORP, 11/6/2022
|  | **Given** a Movie object **when** I instantiate a Screening object **then** I expect to be able to inject a Movie object into multiple Screening objects. | PASS | ORP, 11/6/2022
|  | **Given** I can perform various HTTP requests on Movies **when** I view the list of objects returned **then** I expect to see all the Movie objects. | PASS | ORP, 11/6/2022
Create Movie Model Controller Persistence | As an Owner I want to use SCRUM commands to create, update, get, search, and delete Movie objects so that the proper movies can be on the system which will be used for the screenings. | **GIVEN** I create a Movie object **WHEN** no product of that id exists **THEN** the system should create the product, add it to the persistence, and return a status code of 201 (CREATED) | PASS | ORP, 11/6/2022
|  | **GIVEN** I create a Movie object **WHEN** a product of that id already exists **THEN** the system should return a status code of 409 (CONFLICT) | PASS | ORP, 11/6/2022
|  | **GIVEN** I try to get a Movie **WHEN** it exists **THEN** the system will return the product with a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I try to get a Movie **WHEN** it doesn't exist **THEN** the system will return a status code of 404 (NOT_FOUND) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request for the entire list of Movies **WHEN** movies exist in the persistence file **THEN** the system should return a list of products and a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request for the entire list of Movies **WHEN** no movies exist **THEN** the system should return an empty list of products and a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I search for a movie with a query **WHEN** it exists with the proper id **THEN** the system will return a list of movies that fit the condition | PASS | ORP, 11/6/2022
|  | **GIVEN** I search for a movie with a query **WHEN** it doesn't exist **THEN** the system will return an empty list and a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to update a Movie **WHEN** the movie exists **THEN** the system should update the Movie and return a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to update a Movie **WHEN** the movie doesn't exist** then the system should return a status code of 404 (NOT_FOUND) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to delete a Movie **WHEN** it already exists **THEN** the Movie will be deleted and the system will return a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to delete a Movie **WHEN** it doesn't already exist **THEN** the system will return a status code of 404 (NOT_FOUND) | PASS | ORP, 11/6/2022
See Available Screenings | As a CUSTOMER I want to view all available screenings and their time so that I can decide which one to attend. | **Given** I want to watch a movie **when** I select all movies **then** I expect to see all the available screenings. | PASS | ORP, 11/6/2022
|  | **Given** I want to watch a specific movie **when** I filter results by that movie **then** I expect to see the available screenings of that movie. | PASS | ORP, 11/6/2022
|  | **Given** I want to watch a movie on a specific date **when** I filter results by that date **then** I expect to see the available screenings of all movies on that date. | PASS | ORP, 11/6/2022
Create Angular Setup for Estore | As a product owner I want the webpage to show a set of movies for the user to pick from, with the details of the movies listed below each one. | Given the server is running when I load the webpage then the page with basic UI elements so the user can see all movies. | PASS | ORP, 11/6/2022
|  | Given the server is not running when I load the webpage then I will get a 404-page not found error. | PASS | ORP, 11/6/2022
Create Account Model Controller Persistence | As an Owner I want to use SCRUM commands to create, update, get, search, and delete Account objects so that user accounts can be created through sign up and used to log in. | **GIVEN** I create an Account object **WHEN** no account of that id exists **THEN** the system should create the account, add it to the persistence file, and return a status code of 201 (CREATED) | PASS | ORP, 11/6/2022
|  | **GIVEN** I create an Account object **WHEN** an account of that id already exists **THEN** the system should return a status code of 409 (CONFLICT) | PASS | ORP, 11/6/2022
|  | **GIVEN** I try to get an account **WHEN** it exists **THEN** the system will return the Account with a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I try to get an account **WHEN** it doesn't exist **THEN** the system will return a status code of 404 (NOT_FOUND) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request for the entire list of accounts **WHEN** accounts exist in the persistence file **THEN** the system should return a list of accounts and a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request for the entire list of accounts **WHEN** no accounts exist **THEN** the system should return an empty list of accounts and a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I search for an account with text querying the username **WHEN** an account exists with a username containing the text, **THEN** the system will return a list of accounts that fit the condition | PASS | ORP, 11/6/2022
|  | **GIVEN** I search for an account with text querying the username **WHEN** no such accounts exists, **THEN** the system will return an empty list and a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to update an account **WHEN** the account exists **THEN** the system should update the account and return a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to update an account **WHEN** the account doesn't exist **THEN** the system should return a status code of 404 (NOT_FOUND) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to delete an account **WHEN** it already exists **THEN** the account will be deleted and the system will return a status code of 200 (OK) | PASS | ORP, 11/6/2022
|  | **GIVEN** I submit a request to delete an account **WHEN** it doesn't already exist **THEN** the system will return a status code of 404 (NOT_FOUND) | PASS | ORP, 11/6/2022
Select Tickets | As a CUSTOMER I want to select any number of tickets to a screening so that I can watch a movie (with friends). | **Given** I select a screening **when** I select to purchase tickets **then** I expect to be able to select any number of tickets to a screening. | PASS | ORP, 11/6/2022
|  | **Given** I have selected tickets to a screening **when** I am in the "checkout screen" **then** I expect to be able to increase the number of tickets selected. | PASS | ORP, 11/6/2022
|  | **Given** I have selected tickets to a screening **when** I am in the "checkout screen" **then** I expect to be able to decrease the number of tickets selected. | PASS | ORP, 11/6/2022
|  | **Given** I have selected tickets to a screening **when** I am in the "checkout screen" **then** I expect to be able to remove all my tickets select to abandon the screening. | PASS | ORP, 11/6/2022
Sprint 3 |  |  |  | ORP, 11/6/2022
Create and log into Account | As a CUSTOMER I want to be able to be able to use a button on the website to create, and log into an account so that I can use the features I need to be logged in for. | **Given** I have no user account **when** I complete the sign up process **then** I have an account to log in with | PASS | ORP, 11/6/2022
|  | **Given** I have an account on the website **when** I log in **then** the site shows I am logged in and have the features of being logged in | PASS | ORP, 11/6/2022
Get sorted Screenings | As the OWNER I want to get a sorted list of Screenings so that I can display them to the customer. | **Given** I perform a GET request on Screenings **when** examine the resulting array **then** I expect the objects to be sorted by date. | PASS | ORP, 11/6/2022
|  | **Given** I perform a GET request on Screenings **when** examine the resulting array **then** I expect the objects to be sorted by time. | PASS | ORP, 11/6/2022
Select Screening | As a customer I want to select a screening to a movie so that I can buy tickets to that screening. | **Given** I am on the homepage **when** I click on a movie poster **then** I am taken to select a screening for that movie | PASS | ORP, 11/6/2022
|  | **Given** I am on the screenings page **when** I click on a screening **then** I am taken to select tickets for that screening. | PASS | ORP, 11/6/2022
Track Attendance | As the OWNER I want to track attendance for each screening. | **Given** I want to check on a screening **when** I select on the screening **then** I expect to see how many people bought tickets to the screening. | PASS | ORP, 11/6/2022
Make admin account privileges | As an admin I want to be able to update the inventory so that we can update the server for our products | **Given** I have entered the screening movie information **when** I attempt to add a new screening **then** a new screening will be sent to the server. | PASS | ORP, 11/6/2022
|  | **Given** a movie exists **when** I attempt to delete a screening **then** the screening will be deleted from the server. | PASS | ORP, 11/6/2022
|  | **Given** a movies exists **when** I attempt to change a screening **then** the screening in the server will be updated. | PASS | ORP, 11/6/2022
Create and store customer purchases | As a customer I want to complete a purchase so that I can attend the screening of a movie. | **Given** I am completing an order **when** I am complete a purchase **then** I can add popcorn to my order. | PASS | ORP, 11/6/2022 | Can create order with initial amount, cannot be updated after an order is placed
|  | **Given** I am completing an order **when** I am complete a purchase **then** I can add soda to my order. | PASS | ORP, 11/6/2022 | Can create order with initial amount, cannot be updated after an order is placed
|  | **Given** I am completing an order **when** I am complete a purchase **then** I can add any number of tickets (minimum of 1) to my order. | PASS | ORP, 11/6/2022 | Can create order with initial amount, cannot be updated after an order is placed
Vote/Suggest New Movie | As a CUSTOMER I want to be able to vote on and suggest a new movie to screen so I can watch my favorite movie in the theater. | **Given** I am on the website **when** see a poll for a new movie to screen **then** I can vote on the poll for one of the displayed options. | PASS | GAC, 11/16/2022
|  | **Given** I am on the website **when** see a poll for a new movie to screen **then** I can suggest movies to be added to the poll. | PASS | GAC, 11/16/2022
View User Purchase History | As a CUSTOMER I want to be able to view my purchase history from my account on the website. | **Given** I am logged in to my account **when** I select to view my purchase history **then** I can have a report of my past purchases. | PASS | GAC, 11/16/2022
|  | **Given** I have selected to view my purchase history **when** I select a specific screening **then** I can have a detailed report of the tickets and snacks I purchased for that screening. | PASS | GAC, 11/16/2022
Buy Soda | As a CUSTOMER I want to buy soda so that I can drink while watching the movie. | **Given** I am purchasing movie tickets **when** I reach the order screen **then** I can also select to buy any number of sodas for the screening. | PASS | GAC, 11/16/2022
|  | **Given** I am purchasing movie tickets **when** I reach the order screen **then** I can also select to remove any number of sodas I have previously chosen for the screening. | PASS | GAC, 11/16/2022
Buy Popcorn | As a CUSTOMER I want to buy popcorn so that I can snack while watching the movie. | **Given** I am purchasing movie tickets **when** I reach the order screen **then** I can also select to buy any number of popcorn for the screening. | PASS | GAC, 11/16/2022
|  | **Given** I am purchasing movie tickets **when** I reach the order screen **then** I can also select to remove any number of popcorn I have previously chosen for the screening. | PASS | GAC, 11/16/2022
Buy Tickets 2 (Improving on Select Tickets Story) | As a CUSTOMER I want to buy tickets so that I can go to a screening. | **Given** I am purchasing movie tickets **when** I reach the order screen **then** I can also select to buy any number of tickets for the screening. |  |  | Not implemented yet
|  | **Given** I am purchasing movie tickets **when** I reach the order screen **then** I can also select to remove any number of tickets I have previously chosen for the screening. |  |  | Not implemented yet
Reserve a Seat for Each Ticket | As a CUSTOMER I want to reserve an available seat for each ticket so that I can secure seats for my friends and I to sit at. | **Given** I select an available seat(s) **when** I complete the checkout process **then** I expect the seat to be unavailable for other customers to reserve. |  |  | Not implemented yet
|  | **Given** I release the reserved seats **when** I refund the tickets **then** I expect the seat to become available for other customers to purchase again. |  |  | Not implemented yet
Track Snacks | As the OWNER I want to track how many customers ordered snacks for a screening. | **Given** I want to check on a screening **when** I select a screening **then** I expect to see how many snacks were placed for that screening. |  |  | Not implemented yet
|  | **Given** I want to check on a screening **when** I select a screening **then** I expect to see how many sodas were placed for that screening. |  |  | Not implemented yet
|  | **Given** I release the reserved seats **when** I refund the tickets **then** I expect the seat to become available for other customers to purchase again. |  |  | Not implemented yet
Track Snacks | As the OWNER I want to track how many customers ordered snacks for a screening. | **Given** I want to check on a screening **when** I select a screening **then** I expect to see how many snacks were placed for that screening. |  |  | Not implemented yet
|  | **Given** I want to check on a screening **when** I select a screening **then** I expect to see how many sodas were placed for that screening. |  |  | Not implemented yet